## Slide 1: Business Continuity Systems (Data Recovery Systems)
CS 591 Course Project
Team #06
Nagendra Gangupamu - Class ID = 11
Sai Venkata Nikhil - Class ID = 17
Vega Patel - Class ID = 13

## Slide 2: Index
Contents | Page No
Introduction | 3-4
Software Design and Development Model | 5
Scope Requirements | 6-14
Human Resource Management Plan | 15
Project Cost Estimates | 16-17
Time Management Plan | 18-25
Cost Management Plan | 26-29
Risk Management Plan | 30-36
Procurement Management Plan | 37-38
Statement of Work | 39-40
Request for Proposal | 41
Request for Quote | 42
Conclusion | 

## Slide 3: Business Continuity
Introduction:
Planning to ensure the continuation of operations in the event of a catastrophic event.
Business continuity planning goes beyond disaster recovery planning to include:
• The actions to be taken
• Resources required, and
• Procedures to be followed to ensure the availability of essential services, programs, and operations in the event of unanticipated interruptions.

## Slide 4: Comparison Table
System | eVault | Clearview | Storix | Datto | BCMfort
Main Functions | Authentication Backup Management Controlled Data Access Encryption | Reporting Integration Management Programme Management Offsite Recovery | Adaptable System Recovery Data Cloning Backup Management Disaster Recovery | Data Protection Virtualization Centralized Management Security | Risk Assessment Cost Effective Control Management Security
Scope | End-to-end encryption keeps confidential data safe at every step, and flexible deployment options protect complex, multi-platform sites and distributed networks. With simple pricing and dedicated business support | Clear View represents Making the Complicated Simple of BCM platform which is rapidly being adopted world-wide. Modern yet proven, it helps clients comply with BCM best practice while facing the inevitable need for greater cost-efficiencies | Storix, Inc., providers of disaster recovery solutions for Linux and Unix systems.Storix SBAdmin was one of the first enterprise applications to provide support for Linux on IBM Power systems. | From virtual cloud data to physical endpoint files and the systems that process it all, our total data protection makes your business invincible, secure, and instantly restorable. | BCMfort can ensure that your organization takes a proactive stance to risk management by having controls in place to properly recognize, record and reduce its risk.
Programming Languages used | Java | C# , JAVA | Java | ABAP, Java, C++ | Java , C++
Total Lines of code | 1 Million | 119K | 102K | 334K | 80.5K
Technical Platform | OS: Windows Linux, | .OS: Windows | OS: AIX, Windows Linux, | OS: Windows, Unix | OS: Windows Linux,
 | Server: Apache Server | Server: Apache Server | Server: Apache Server | Server: Tomcat Server | Server: Apache Server
 | DB: mysql Server | DB: mysql Server | DB: mysql Server | DB: mysql ServerNet Server 3.0 | DB: MySQL Server
Website for downloadable version of trial software | https://www.evault.com/platform/technologies/ | http://www.clearview-continuity.com/ | http://www.storix.com/sbadmin-support/free-trial | http://www.datto.com/technologies/backup-insights | https://bcmfort.com/services/

## Slide 5: Software Design and Development Model

## Slide 6: Business Continuity Planning Scope
Functional Requirements :
• Business Rules • Transaction Requirements • Administrative Functions • Authentication • Authorization Levels • Reporting Requirements • Audit Tracking • External Interfaces • Risk Evaluation • Business Impact Analysis • Recovery Strategy • Testing and Maintenance

## Slide 7: Business Continuity Planning Scope (cont.)
Non-Functional Requirements:
  Availability: 99.999% uptime
  Scalability: Easily scalable to over 10,000 users and over 2,000,000 records
  Recoverability: Ability to restore your deployment to the point at which a failure occurred.
  Backups: We should be able to download full database backups on a daily basis
  Disaster Recovery: Redundant data centers needed to minimize impact of disaster upon information and data required for critical business processes.

## Slide 8: Business Continuity Planning Scope (cont.)
Technical Platform:
  Web Server: Apache Server
  Database: MySQL
  Operating System: Windows, Unix, Linux.
  Language: Built on J2EE Framework, JAVA.

## Slide 9: Work Breakdown Structure

## Slide 10: Work Breakdown Structure

## Slide 11: Roles and Responsibility Matrix
Activity | Quality Manager | Project Manager 1 | Project Manager2 | Project Manager 3 | Project Manager4 | System Analyst1 | System Analyst 2 | System Analyst 3 | System Analyst 4 | System Analyst 5 | Developer1 | Developer2 | Developer3 | Developer4
1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1.1 |  | A | R | R |  |  |  | I |  | I |  |  | I | 
1.1.2 |  | A | R | R |  |  |  |  |  |  | I | I | I | I
1.1.3 |  | R | R | A |  | R |  |  |  |  | I | I | I | I
1.1.4 |  | A | R | R | C | R |  |  | ] |  | I | I | I | I
1.1.5 | A | R | R | R | R | I | I | I | I | I | I | I | I | I
1.2 |  | A | C | R |  | I | I | I | I | I | I | I | I | I
1.2.1 |  | A |  | R | I |  | I | I | I | I | I | I | I | I
1.2.2 |  | R | A |  |  | R | R | I | I | I | I | I | I | I
1.2.3 |  | R | R | A | I | R | R | I | I | I | I | I | I | I
1.2.4 |  | A | C | R | C |  | R | R | R |  | I | I | I | I
1.2.5 |  | R | A |  | R |  | R | R |  |  | I | I | I | I
1.2.6 |  | A | C | R | I | R | C | R |  | R | I | I | I | I
1.2.7 |  | A | R |  | C | R | R | R | I | I | I | I | I | I
1.2.8 | A | R | R | R | R | C | C | I | I | I | I | I | I | I
1.3 |  | C | C |  | C | C | C | C | I | I | I | I | I | I
1.3.1 |  | R | A |  |  | R | R | C | I | I | I | I | I | I
1.3.1.1 |  | A | R | C | R | R | C | R | I | I | I | I | I | I
1.3.1.2 |  | R | A |  | I | R | R | R |  |  | R | R | R | R

## Slide 12: Roles and Responsibility Matrix
Activity | Quality Manager | Project Manager 1 | Project Manager2 | Project Manager 3 | Project Manager4 | System Analyst1 | System Analyst 2 | System Analyst 3 | System Analyst 4 | System Analyst 5 | Developer1 | Developer2 | Developer3 | Developer4
1.3.1.3 |  | R | C |  |  | I | R | I |  |  | I | R | R | 
1.3.1.4 |  | A |  |  |  | I | I | I |  |  | I | R | I | 
1.3.1.5 |  |  |  |  |  |  |  | R | R |  |  |  | R | 
1.3.1.6 |  | A |  | R |  |  |  |  |  |  | I | I | R | R
1.3.1.7 | A | R |  | R |  |  |  | R |  |  | I | I | I | 
1.3.2 |  | R | A |  |  |  |  |  | R |  | I | I | I | 
1.3.2.1 |  |  |  |  |  | R | I | I |  |  | R | I | I | 
1.3.2.2 |  | C | R | A |  | I | I | I |  | R | R | R | R | R
1.3.2.3 |  | C |  |  |  |  | R | I |  |  | I | R | R | 
1.3.2.4 |  | A | R | R |  | R | R | I | I |  | I | R | I | 
1.3.2.5 |  |  | C |  | R |  |  | R | R |  | I | I | R | 
1.3.2.6 |  | C | A |  | R |  |  | R | R | R | R | I | I | 
1.3.2.7 | A | R | C | R |  |  | R | R |  |  | I | I | I | 
1.3.3 |  | C | C |  |  | R | C | R |  | R | I | I | I | 
1.3.3.1 |  | A |  | R |  | R | I | I |  |  | R | I | I | 
1.3.3.2 |  | C | R |  |  | I | I | I |  |  | R | R | R | R
1.3.3.3 |  |  |  |  |  |  | R | I |  |  | I | R | R | 
1.3.3.4 |  | C | C |  |  | R | R | I |  |  | I | R | I | 
1.3.3.5 |  |  | A |  | R |  |  | R | R |  | I | I | R | 
1.3.3.6 |  | C | C |  |  |  |  | R | R | R | R | I | I | 
1.3.3.7 | A | R |  | R |  |  | R | R |  |  | I | I | I | 

## Slide 13: Roles and Responsibility Matrix
Activity | Quality Manager | Project Manager 1 | Project Manager2 | Project Manager 3 | Project Manager4 | System Analyst1 | System Analyst 2 | System Analyst 3 | System Analyst 4 | System Analyst 5 | Developer1 | Developer2 | Developer3 | Developer4
1.3.14 |  | R | C |  |  | I | I | I |  |  | I | I | I | 
1.3.14.1 |  | A |  | R |  | R | I | I |  |  | R | I | I | 
1.3.14.2 |  | C | R |  |  | I | I | I |  |  | R | R | R | R
1.3.14.3 |  | R |  | C |  |  | R | I | I |  | I | R | R | 
1.3.14.4 |  | C | C |  | A | R | R | I |  |  | I | R | I | 
1.3.14.5 |  | A | A |  |  |  |  | R | R |  | I | I | R | 
1.3.14.6 |  | C | C |  |  |  |  | R | R | R | R | I | I | I
1.3.14.7 | A | R |  | R | C |  | R | R |  |  | I | I | I | 
1.3.15 |  |  |  | R |  |  | I | I |  |  | I | I | I | 
1.4 |  | C | R | R |  |  |  | I |  |  | I | I | I | I
1.5 | A | R | R |  | C |  |  | I | I |  | I | I | I | 

## Slide 14: Required Resources

## Slide 15: Required Human Resources
S.No | Job Title | Resources
1 | Quality Manager | Laptop5, Cellphone5, PDA5
2 | Project Manager1 | Laptop1,Cellphone1,PDA1
3 | Project Manager2 | Laptop2,Cellphone2, PDA2
4 | Project Manager3 | Laptop3,Cellphone3, PDA3
5 | Project Manager4 | Laptop4,Cellphone4, PDA4
6 | System Analyst1 | Laptop6,Cellphone6
7 | System Analyst2 | Laptop7,Cellphone7
8 | System Analyst3 | Laptop8,Cellphone8
9 | System Analyst4 | Laptop9,Cellphone9
10 | System Analyst5 | Laptop10,Cellphone10
11 | Developer1 | Desktop1
12 | Developer2 | Desktop2
13 | Developer3 | Desktop3
14 | Developer4 | Desktop4

## Slide 16: Cost Estimates – LOC Based Estimation
Function | Pages | Lines of Code Per Page | Total Lines of Code(TLOC)
User Interface for Static Pages | 51 | 327 | 16677
User Interface for Dynamic Pages | 47 | 297 | 13959
Code Behind Static Pages | 81 | 222 | 17982
Code Behind Dynamic Pages | 85 | 311 | 26435
Database- SQL Stored Procedures | 34 | 291 | 9894
Business Layer-Logical Pages | 21 | 228 | 4788
Other Layer-Logical Pages | 17 | 115 | 1955
 |  | Total | 91690
Estimating $12 per line of code |  | Total Project Cost | 1,100,280

## Slide 17: FP Based Estimation
Total Functional points = 896
Average Cost per functional point is 1230
Estimated Project Cost= 896*1230 = $1,102,080
Category | Low | Weight_L | Average | Weight_A | High | Weight_H | Total (T)
User inputs | 21 | 3 | 10 | 5 | 5 | 4 | 133
User outputs | 13 | 3 | 15 | 8 | 7 | 8 | 241
User inquires | 15 | 4 | 13 | 3 | 9 | 4 | 135
File/Structures | 16 | 7 | 12 | 5 | 8 | 5 | 212
External Interface | 10 | 6 | 14 | 5 | 5 | 9 | 175
Unadjusted Total (UT): |  |  |  |  |  |  | 896

## Slide 18: Time Management Plan – Project tasks

## Slide 19: Time Management Plan – Project tasks (Cont.)

## Slide 20: Time Management Plan – Project tasks (Cont.)

## Slide 21: Time Management Plan – Project tasks (Cont.)

## Slide 22: Time Management Plan – Project tasks (Cont.)

## Slide 23: Time Management Plan – Project tasks (Cont.)

## Slide 24: Time Management Plan – Gantt Chart

## Slide 25: Time Management Plan
Phases | Start Date | Final Date | Duration(Days)
1.1 Project Initiation | 8/24/2016 | 10/3/2016 | 29
1.2 Project Plan | 10/4/2016 | 11/21/2016 | 35
1.3.1 Release 1 | 11/22/2016 | 12/9/2016 | 14
1.3.2 Release 2 | 12/12/2016 | 12/28/2016 | 13
1.3.3 Release 3 | 12/29/2016 | 1/16/2017 | 13
1.3.4 Release 4 | 1/17/2017 | 2/1/2017 | 12
1.3.5 Release 5 | 2/2/2017 | 3/1/2017 | 20
1.3.6 Release 6 | 3/2/2017 | 3/23/2017 | 16
1.3.7 Release 7 | 3/24/2017 | 4/11/2017 | 13
1.3.8 Release 8 | 4/12/2017 | 5/5/2017 | 18
1.3.9 Release 9 | 5/8/2017 | 6/1/2017 | 19
1.3.10 Release 10 | 6/2/2017 | 6/20/2017 | 13
1.3.11 Release 11 | 6/21/2017 | 7/20/2017 | 22
1.3.12 Release 12 | 7/21/2017 | 8/8/2017 | 13
1.3.13 Release 13 | 8/9/2017 | 9/14/2017 | 27
1.3.14 Release 14 | 9/15/2017 | 10/12/2017 | 20
Overall Project | 8/24/2016 | 10/13/2017 | 298

## Slide 26: Cost Management Plan
Resource Name | Type | Initials | Max. Units | Std. Rate
Quality Manager | Work | P | 100% | 64.12$/hr
Project Manager1 | Work | P | 100% | 68.56$/hr
Project Manager2 | Work | P | 100% | 61.20$/hr
Project Manager3 | Work | P | 100% | 59.32$/hr
Project Manager4 | Work | P | 100% | 62.30$/hr
System Analyst1 | Work | S | 100% | 56.35$/hr
System Analyst2 | Work | S | 100% | 52.16$/hr
System Analyst3 | Work | S | 100% | 47.23$/hr
System Analyst4 | Work | S | 100% | 49.21$/hr
System Analyst5 | Work | S | 100% | 55.65$/hr
Developer1 | Work | D | 100% | 47.32$/hr
Developer2 | Work | D | 100% | 46.89$/hr
Developer3 | Work | D | 100% | 50.19$/hr
Developer4 | Work | D | 100% | 53.67$/hr

## Slide 27: Cost Management Plan – Material Resources
Resource Name | Type | Initials | Std. Rate
Laptop1 | Material | L | 2200$
Laptop2 | Material | L | 2200$
Laptop3 | Material | L | 2200$
Laptop4 | Material | L | 2200$
Laptop5 | Material | L | 2200$
Laptop6 | Material | L | 2000$
Laptop7 | Material | L | 2000$
Laptop8 | Material | L | 2000$
Laptop9 | Material | L | 2000$
Laptop10 | Material | L | 2000$
Desktop1 | Material | D | 1500$
Desktop2 | Material | D | 1500$
Desktop3 | Material | D | 1200$

## Slide 28: Cost Management Plan – Material Resources
Resource Name | Type | Initials | Std. Rate
Desktop4 | Material | D | 1200$
Cellphone1 | Material | C | 200$
Cellphone2 | Material | C | 170$
Cellphone3 | Material | C | 150$
Cellphone4 | Material | C | 150$
Cellphone5 | Material | C | 120$
Cellphone6 | Material | C | 100$
Cellphone7 | Material | C | 150$
Cellphone8 | Material | C | 80$
Cellphone9 | Material | C | 80$
Cellphone10 | Material | C | 200$
PDA1 | Material | P | 200$
PDA2 | Material | P | 200$
PDA3 | Material | P | 150$
PDA4 | Material | P | 150$
PDA5 | Material | P | 170$

## Slide 29: Cost Management Plan – Material Resources
Task# | Task Name | Estimated Budget
1 | Project Initiation | $65,181.44
2 | Project Plan | $86,516.96
3 | Release1 | $63,729.60
4 | Release2 | $61,806.40
5 | Release3 | $60,484.08
6 | Release4 | $59,729.60
7 | Release5 | $74,867.28
8 | Release6 | $67,390.96
9 | Release7 | $61,730.00
10 | Release8 | $70,221.44
11 | Release9 | $71,194.40
12 | Release10 | $61,730.00
13 | Release11 | $76,712.48
14 | Release12 | $61,730.00
15 | Release13 | $83,904.32
16 | Release14 | $73,466.96
17 | Project Closeout | $5,972.96
 | Total Cost | $1,106,368.88

## Slide 30: Risk Management Plan – Decision Tree
Key piece of software
Initial Question
Options
Probabilities
Outcomes
In house development
outsource
CF = 0.4
PS = 0.25
CS = 0.35
CF = 0.6
CS = 0.4
Expected Values
$1,174,334.32*0.25 = $293,583.58
$1,106,368.88*0.35 = $387,229.1
Total = $254,775.15
$1,065,093.84*0.6 = $639,056.3
$1,142,696.23*0.4 = $457,078.49
Total = $181,977.8
$1,065,093.84
$1,174,334.32
$1,106,368.88
$1,065,093.84
$1,142,696.23
$1,065,093.84*0.4 = $426,037.53

## Slide 31: Risks in Business Continuity

## Slide 32: Risks in Business Continuity

## Slide 33: Risk Management Plan – Risk Exposure Table
Risk No. | Risk Drivers | Description | Risk Probability (RP) | Risk Impact (RI) | Risk Exposure (RP * RI)
1 | Experience and Teaming | Limited software experience in the project office. Software staff not included in early planning and design decisions. | Medium(0.5) | Medium High(0.7) | 0.35
2 | Requirements and Design | Systems decisions made without accounting for impact on software. Poor scope definition. | High(0.9) | High(0.9) | 0.81
3 | Planning | Lack of appropriate planning detail with insufficient reviews. Unclear SOW and WBS. | Medium Low(0.3) | Medium Low(0.3) | 0.09
4 | Testing | Plan to convert SW test documents not due till very late in the life-cycle.developers into test team late in life-cycle. | Medium High(0.7) | Medium High(0.7) | 0.49
5 | Tools | Limited test analysis tools. Unproven design tools selected with limited time for analysis. | Low(0.1) | Medium Low(0.3) | 0.03
6 | Schedule | Schedule changes - with the possibility of scope changes and other issues, schedule changes may also be needed. | Medium High(0.7) | Medium Low(0.3) | 0.21

## Slide 34: Risk Management Plan – Probability Matrix
IMPACT | LOW | LOW MEDIUM | MEDIUM | MEDIUM HIGH | HIGH
PROBABILITY |  |  |  |  | 
LOW |  | 3 |  |  | 
LOW MEDIUM |  |  | 2 |  | 
MEDIUM | 4 |  |  |  | 
MEDIUM HIGH |  |  |  | 1 | 
HIGH |  |  | 5 | 6 | 7
 | IMPACT | PROBABILITY
1.Key piece of code construction outsourced | Medium high | Medium high
2.Budget constraints | Medium | Medium Low
3.Poorly understood requirements | Medium low | Low
4.Change Management | Low | Medium
5.Some Key Users Located in a different location from IT staff | Medium | High
6.Technology used for development is new to IT staff | Medium high | High
7.Project manager assigned to project is new to the company | High | High

## Slide 35: Risk Management Plan
Case # | Project Total Cost | Risk Factor | Duration (Days) | Probability | Expected Value
 | (Data will be obtained during Lab 3) | (Data must be calculated before the Lab 3) | (Data will be obtained during Lab 3) | (Data will be given by Instructor before Lab 3) | (Data will be calculated during Lab 3)
0 | $1,106,368.88 | 1.62 | 298 |  | 
1 (Remove 1 expert (8-9 yrs exp) - 1SA) | $1,093,152.88 | 1.9 | 298 | Partial Failure (35%) | ($4,625.60)
2 (Remove 2 experts(8-9 yrs exp) 1SA, 1 Devloper) | $1,065,093.84 | 2.2 | 310.67 | Complete Failure (30%) | ($12,382.51)
3 (add experts - 1tester, 1developer) | $1,142,696.23 | 0.94 | 289.67 | Complete Success (20%) | $7,265.47
4(add beginners - 1PM, 1SA, 1tester, 1 developer) | $1,174,334.32 | 1.28 | 282.07 | Partial Success (15%) | $10,194.82
 |  |  |  | EMV | $452.17
 |  |  |  | Total EMV | $1,106,821.05
 |  |  |  |  | So from a risk perspective, this project is worth doing.

## Slide 36: Risk Management Plan- Risk Factors and Graphs
Chart: Risk Factor Vs Duration Vs Cost
| Project total cost | $10,65,093.84 | $10,93,152.88 | $11,06,368.88 | $11,42,696.23 | $11,74,334.32
Project total Duration | 310.67 | 298 | 298 | 289.67 | 282.07
Project risk Factor | 2.2 | 1.9 | 1.62 | 0.94 | 1.28
Chart: 
| 2 | 1 | 0 | 3 | 4
Project total cost vs Case# | 1065093.84 | 1093152.88 | 1106368.88 | 1142696.23 | 1174334.32
Chart: 
| 2 | 1 | 0 | 3 | 4
Project risk Factor vs Case# | 2.2 | 1.9 | 1.62 | 0.94 | 1.28
Chart: 
| 2 | 1 | 0 | 3 | 4
Project total Duration vs Case# | 310.67 | 298 | 298 | 289.67 | 282.07

## Slide 37: Procurement Management – Make Or Buy Diagram
BCP SYSTEM
Build
Reuse
Buy
Contract
0.6
0.4
0.4
0.6
0.7
0.3
0.35
0.65
904369
1289348
1098454
1140469
1194172
1266098
1179279
1284340
542621.4
515739.2
659072.4
456187.6
358251.56
886269.2
412747.95
834821.5
Expected cost for build:
542621.4+515739.2
=$1058360.6
Expected cost for Reuse:
659072.4+456187.6
=$1115260
Expected cost for Buy:
358251.56+886269.2
=$1244520.76
Expected cost for Contract: 412747.95+834821.5
=$1247569.45

## Slide 38: Procurement Management Plan
If Project is Completed by Seller at $1,106,368.88
If Project Completed by Seller at $1,156,368.88
Sharing formula : 80/20
Allowable cost: $1,120,000
Maximum Fee: $80,000
Minimum Fee: $20,000
Target fee : $50,000
Computations:
$1,106,368.88 +[$1,120,000- $ 1,106,368.88]*0.20+50,000 = $1,159,095.1
Profit: $52,726.2
Sharing formula : 80/20
Allowable cost: $1,120,000
Maximum Fee: $80,000
Minimum Fee: $20,000
Target fee : $50,000
Computations:
$1,156,368.88 + $20,000 = $1,176,368.88
Profit: $20,000

## Slide 39: Statement of Work
Project Name: Business Continuity Planning
Customer: IT Organization
Project Start Time: Wed 08/24/16
Project End Time: Fri 10/13/17
Project Implementation Estimates:
Project Initiation: Wed 8/24/16 to Mon 10/3/16
Project Plan: Tue 10/4/16 to Mon 11/21/16
Release1: Tue 11/22/16 to Fri 12/9/16
Release 2: Mon 12/12/16 to Wed 12/28/16
Release 3: Thu 12/29/16 to Mon 1/16/17
Release 4: Tue 1/17/17 to Wed 2/1/17
Release 5: Thu 2/2/17 to Wed 3/1/17
Release 6: Thu 3/2/17 to Thu 3/23/17
Release 7: Fri 3/24/17 to Tue 4/11/17
Release 8: Wed 4/12/17 to Fri 5/5/17
Release 9: Mon 5/8/17 to Thu 6/1/17
Release 10: Fri 6/2/17 to Tue 6/20/17
Release 11: Wed 6/21/17 to Thu 7/20/17
Release 12: Fri 7/21/17 to Tue 8/8/17
Release 13: Fri 8/4/17 to Wed 9/13/17
Release 14: Thu 9/14/17 to Wed 10/11/17

## Slide 40: Statement of Work(cont.)
Project Description: Business Continuity Planning (BCP) is a structured framework for identifying the risk posed to an organization via internal and external threats
Goal: BCP should be able to provide a shield and protect the organization from threats such as natural disasters or data breaches and also the business interests of the Organization.
Objective: Analyzing and understanding continuity needs and establishing realistic business continuity planning policies. Implementation of controls and measures to manage overall continuity risks of an organization.
Operating, Monitoring and performance evaluation of business continuity planning system.
Phases Of Work: Pre-Evaluation Screening, Planning Phase, Testing, End-user Training, Post-Implementation

## Slide 41: Request for Proposal
Background: Team_06_CS591 is developing BCP system. The validation is outsourced to eligible agency. The solely purpose of the document is to request a quote for the execution of validation phase of BCP system software development.
Objective: The objective to obtain statement of work for validation test for BCP system.
Schedule: Bids shall be firm offers and shall remain valid for acceptance 60 days following the RFQ closing date. RFQ closing date – October 13, 2017
Statement of work: Detailed enclosed in Statement of work
Technology Constraints: Detailed enclosed in Statement of work
Evaluation Criteria:
Contract award in best interest Team_06_CS591 reserves the right to accept or reject proposal on each item separately or as a whole. The team also reserves the right to award any resultant contract as a whole, or split award between bidders.
Bid Rejections Failure to use the bid form furnished by our team Failure to sign the bid by authorized representatives.
Late or incomplete bid.
Contract award Team_06_CS591 reserve the right to negotiate modification of the bid prices, terms and conditions with lowest responsive bidder.
Vendor: The Vendor shall provide three references to contract for further processes.
Evaluation Criteria Each RFQ response will be evaluated on the bases of the following criteria list in order of importance:
Based on experience, cost and time.

## Slide 42: Request For Quote
Item | Description | Unit Cost | Extended Cost
1 | Unit Test case design, test script, results, supporting document and traceability of software design. |  | 
2 | Software integration test design, test case, results, supporting documentations and traceability to software design |  | 
3 | System integration test design, test case, results and supporting documentations traceability to high level system requirements. |  | 
Send completed bids to:
Team_06_CS591
Bradley University,
Peoria, IL, 61625
Additional Information contact:
BCP Support
Bradley University,
Peoria, IL, 61625

## Slide 43: Thank You !